## 00 Import notes
IMPORT - deselect this sheet when importing into STG Checklist
Plan name: STG Health - ultra competitive top 10
Source: docs/2026-06-07_stg_health_competitive_features_roadmap.md, docs/2026-06-07_Health_and_Nutrition_Apps_Comparison.xlsx
Each other sheet = task group; column A = task; column B = notes (optional).
Track completion of the roadmap Top 10 features (P0-P2).
Sheet 01 = milestone checkboxes; sheets 02-04 = implementation subtasks.
Column B notes import into each task item in STG Checklist (editable after import).
Mark [DONE] or [PARTIAL] prefix in column A when re-exporting from Excel.

## 01 Top 10 milestones
Task | Notes
[DONE] UC-01: Barcode scanner for packaged foods | Priority: P0 Closes gap vs: MyFitnessPal, Lose It!, Lifesum, Fitbit Suggested tier: Standard Purpose: Let users log packaged foods by scanning UPC/EAN instead of typing brand names - table stakes for 2026 nutrition apps. What it will do: Camera scan on iOS/Android -> lookup local USDA FTS catalog -> Open Food Facts or branded USDA fallback for misses -> nutrition preview (calories, protein/carbs/fat) -> confirm portion -> add to selected meal and day. Unknown barcode: prompt manual search; optional "request food" hook later. Acceptance criteria: Scan UPC -> matched item -> user confirms serving -> saved to meal log without leaving food flow. Likely touch points: lib/features/food/, food_search_field.dart, food_item_repository.dart, catalog import; mobile_scanner or ML Kit; entitlements in app_config.dart.
[DONE] UC-02: Apple Health + Google Fit sync | Priority: P0 Closes gap vs: Apple Health, Google Fit, Samsung Health, Fitbit, MyFitnessPal Suggested tier: Standard Purpose: Close the "no ecosystem integration" gap while staying local-first - read/write key metrics from platform health stores instead of building a wearable stack. What it will do: iOS/macOS: Apple HealthKit via health package - weight, dietary energy, water, steps, sleep duration, workouts. Android: Health Connect - same metric set. Profile screen: connect/disconnect, permissions, last sync timestamp, manual "Sync now". Imported steps/workouts merge with manual exercise log; weight writes back when user logs in app. Acceptance criteria: After user grants permissions, weight/steps/sleep hours appear in app within one sync cycle; outbound weight log updates Health when enabled. Likely touch points: New lib/features/health_sync/; profile settings; weekly summary report (sleep hours); exercise merge logic.
[DONE] UC-03: Water logging + daily hydration goal | Priority: P0 Closes gap vs: MyFitnessPal, Lose It!, Lifesum, Samsung Health, Fitbit Suggested tier: Standard Purpose: Daily water tracking is expected in every major calorie app; STG currently has no hydration surface. What it will do: Log water intake in ml or US cups; daily running total vs profile hydration goal. Quick-add buttons on home and/or food area (e.g. 8 oz, 12 oz, 250 ml, 500 ml). Optional sync write/read via Health platforms when UC-02 ships. Show progress bar or ring on home dashboard. Acceptance criteria: User can add water in two taps; daily total and goal % visible on home; persists in SQLite offline. Likely touch points: New log type or stgh_daily_* extension; home_page.dart; profile hydration goal field; Health sync (UC-02).
[DONE] UC-04: Photo / meal-scan assist for food logging | Priority: P1 Closes gap vs: Lose It!, MyFitnessPal Premium Suggested tier: Premium (candidate) Purpose: Reduce friction for restaurant and homemade meals where barcode and search fail - competitive with premium tiers, not day-one table stakes. What it will do: User photographs plate -> on-device or API vision model returns top 3 food hypotheses with estimated portions. User confirms/edits selection before save (never auto-log without confirm). Ship after barcode + search are solid; gate behind Premium entitlement. Acceptance criteria: Photo -> suggestions list -> user picks one -> portion confirm -> meal entry saved; failures show friendly fallback to search. Likely touch points: lib/features/food/ camera flow; optional cloud vision API; app_config Premium gate.
[DONE] UC-05: Adaptive calorie goal (expenditure trend) | Priority: P1 Closes gap vs: MacroFactor, Lose It! forecasting Suggested tier: Standard Purpose: Differentiate with smart metabolism tooling - suggest calorie target from actual weight trend + logged intake, without guilt-based coaching. What it will do: Weekly engine: compare smoothed weight change to average logged calories -> estimate maintenance expenditure -> suggest adjusted daily calorie goal. Optional toggle in profile ("Use adaptive recommendation"); show explanation of math in plain language. Does not auto-change goal without user accept. Acceptance criteria: After 2+ weeks of weight + food data, app shows a reasoned weekly calorie suggestion user can apply or dismiss. Likely touch points: New adaptive calorie service; weight logs + food totals aggregation; profile_page.dart; home summary.
[DONE] UC-06: Body measurements beyond weight | Priority: P1 Closes gap vs: Cronometer, Lifesum, Lose It! Suggested tier: Standard Purpose: Weight alone is insufficient for users tracking composition; competitors expose waist and body fat %. What it will do: On weight log entry: optional waist circumference, body fat %, lean mass notes. Optional progress photo attach (local file path only - no cloud upload in v1). Display latest measurements in weight report and profile summary. Acceptance criteria: User can save waist/body fat with a weigh-in; values appear in Weight & BMI report sections. Likely touch points: Weight log UI; stgh weight-related tables; health_report_builders.dart; local photo storage path.
[DONE] UC-07: Vitals UI (BP, pulse, glucose optional) | Priority: P1 Closes gap vs: Cronometer, Samsung Health Suggested tier: Standard Purpose: Schema (stgh_vital_log) exists but no UI - matrix marks "other health metrics" as a STG gap vs Cronometer. What it will do: Dedicated vitals log page: blood pressure (systolic/diastolic), resting pulse, optional blood glucose. List + add + edit + delete with date/time; optional import from Health if metric present. Include vitals summary section in Health Dashboard report. Acceptance criteria: User logs BP reading -> appears in history -> exports to PDF/Markdown report. Likely touch points: stgh_vital_log table; new vitals_log_page.dart; router.dart; report builders; Health sync read path.
UC-08: Micronutrient display (extend USDA catalog) | Priority: P2 Closes gap vs: Cronometer Suggested tier: Premium (micro report) / Standard (top micros on day view) Purpose: Cronometer's moat is micronutrient depth; STG has USDA fields in catalog but does not surface them - "Cronometer-lite" is enough for niche leadership. What it will do: Day view: show top micros (fiber, sodium, key vitamins/minerals) vs simple RDA targets from USDA portion data. Report: "Micronutrient summary" - top 10 micros vs RDA for selected period (Premium). Extend catalog import to ensure micro fields populated for common foods. Acceptance criteria: Logged meals aggregate to daily micro totals; report lists top 10 micros with % RDA. Likely touch points: food_item / catalog schema; daily aggregation; new micronutrient report kind; entitlements.
[DONE] UC-09: Motivational progress UX (milestones, goal date, smoothing) | Priority: P2 Closes gap vs: Lose It!, Lifesum Suggested tier: Standard Purpose: Users expect visual progress, forecast goal date, and light milestones - without Noom-style psychology or social feeds. What it will do: Explicit target weight + target date on profile; progress % toward goal. 7-day exponential moving average weight curve on home and Weight & BMI report. Estimated goal date at current rate (Lose It!-style). Lightweight milestones (5 lb, 10 lb, etc.) and optional weigh-in / logging streaks - neutral copy only. Acceptance criteria: Profile shows target weight/date; home shows smoothed trend + forecast date; milestone toast or badge on threshold cross. Likely touch points: profile_page.dart; health_report_helpers.dart; home_page.dart; weight report charts.
[DONE] UC-10: Web write path or consumer cloud backup | Priority: P2 Closes gap vs: MyFitnessPal Web, Cronometer Web Suggested tier: Premium (cloud backup) / Standard (read-only web stays if backup deferred) Purpose: Web is read-only today; competitors offer full browser logging or cloud continuity - pick one path for parity without abandoning privacy story. What it will do: Option A - Web write: authenticated browser logging against user account (WP API / sync layer evolution). Option B - Consumer cloud backup: optional encrypted backup to STG cloud or user-owned S3; restore on new device. Product decision required; implement one path first. Local-first remains default; sync is opt-in. Acceptance criteria: User can either log a meal from web OR schedule encrypted backup and restore on second device - documented privacy model. Likely touch points: stg_health web build; WP API; backup settings page; entitlements; encryption design doc.

## 02 P0 implementation
Task | Notes
[DONE] UC-01a: Add barcode scanner dependency + camera permissions (iOS/Android) | Integrate mobile_scanner or ML Kit; Info.plist / Android manifest permissions; graceful deny flow.
[DONE] UC-01b: UPC lookup pipeline (USDA FTS -> Open Food Facts fallback) | Service: normalize UPC, query local catalog, OFF API on miss, map to food_item row shape.
[DONE] UC-01c: Scan UI in food logging flow with portion confirm | Entry point from food log FAB or search; preview macros; add to breakfast/lunch/dinner/snack.
[DONE] UC-02a: Apple HealthKit read/write (weight, energy, water, steps, sleep, workouts) | health package; permission UX; background sync policy; conflict rules vs manual entries.
[DONE] UC-02b: Android Health Connect integration (same metrics as iOS) | Health Connect SDK; parity matrix documented in profile help text.
[DONE] UC-02c: Health sync settings on profile (connect, sync now, last sync) | Toggle per metric family; show errors; audit log optional.
[DONE] UC-03a: Water log storage + daily aggregation query | Schema decision: dedicated water log table or daily summary columns; repository + tests.
[DONE] UC-03b: Hydration goal on profile + quick-add on home | Goal in ml/cups respecting unit system; preset buttons; progress indicator.

## 03 P1 implementation
Task | Notes
[DONE] UC-04a: Photo capture UI + food hypothesis picker (Premium gate) | Camera plugin; top-3 results; manual override to search.
[DONE] UC-05a: Adaptive calorie engine + weekly suggestion card | Weight trend + intake averages; user accept/dismiss; explain calculation.
[DONE] UC-06a: Extended weight entry fields (waist, body fat %) | Form fields + validation; show in reports.
[DONE] UC-06b: Optional progress photo on weight entry (local storage) | File picker/camera; store under app documents; thumbnail in weight history.
[DONE] UC-07a: Vitals log page (BP, pulse, optional glucose) | CRUD UI on stgh_vital_log; router + drawer link; unit labels.
[DONE] UC-07b: Vitals section in Health Dashboard report | Aggregate latest readings per user filter; PDF/Markdown export.
[DONE] UC-05b: 7-day weight EMA + goal date forecast (feeds UC-09) | health_report_helpers + home sparkline; shared with motivational UX.

## 04 P2 implementation
Task | Notes
UC-08a: Daily top-micros panel on home (fiber, sodium, etc.) | Aggregate from logged foods using USDA micro fields.
UC-08b: Micronutrient summary report (top 10 vs RDA) | New report kind; Premium gate per pricing analysis.
[DONE] UC-09a: Target weight + target date on profile | Fields + progress %; feeds forecast copy.
[DONE] UC-09b: Milestones + logging streaks (neutral UX) | 5/10 lb badges; weigh-in streak; no guilt strings.
[DONE] UC-10a: Product decision: web write vs encrypted cloud backup | One-pager with privacy implications; pick v1 scope.
[DONE] UC-10b: Implement chosen UC-10 path (web write OR backup/restore) | MVP for selected option; entitlements + user docs.